## Project Backlog
User Stories
ID | Feature | As a(n) <actor> | I would like to <description> | So that I can | Estimate (hours) | Assigned To | Sprint #
1 | Home & Registration Pages | app user | register an account | login | 8 | Dakoda | 1
2 | Login Page | app user | login | gain access to the game | 4 | Jamie | 1
3 | Game Board | app user | start a game | see the game board | 7 | Jamie | 2
4 | Game Board | app user | click the buttons on the board | interact with the game | 6 | Dakoda | 2
5 | Optimization | developer | remove full page resreshes in when a user click a cell on the game board | save memory and create a smoother user experience | 6 | Dakoda | 3
6 | Game Board | app user | right click on the game board to place a flag | keep track of potential bombs on the board not be able to left click that cell | 4 | Dakoda | 3
7 | Results | app user | display when I win or lose a game | see my results when the game is over | 2 | Jamie | 3
8 | Refactoring and Code Cleanup | developer | perform occasional refactoring and cleanup | maintain a clean code base | 8 | Jamie | 3

## Burn Down Chart
Project: | Minesweeper
Sprint # | 1
[5 empty] | DATE: | 2023-11-27 | 2023-11-28 | 2023-11-29 | 2023-11-30 | 2023-12-01 | 2023-12-02 | 2023-12-03
| User Story ID | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| 1 | As a user, I would like to be able to register an account so that I can login. | build controller | Dakoda | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1
|  |  | build model | Dakoda | 2 | 0 | 0 | 0 | 0 | 0.5 | 1 | 0.5
|  |  | build views | Dakoda | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 3
| 2 | As a user, I would like to be able to login so that I can access the game | build views | Jamie | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
|  |  | build model | Jamie | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  |  | build controller | Jamie | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
|  |  | build database | Jamie | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Ideal - Remaining efforts in uninterrupted working hours. |  |  |  | 14 | 12 | 12 | 11 | 9 | 6 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours. |  |  |  | 14 | 14 | 14 | 14 | 14 | 13.5 | 4.5 | 0
Project: | Minesweeper
Sprint # | 2
[5 empty] | DATE: | 2023-12-04 | 2023-12-05 | 2023-12-06 | 2023-12-07 | 2023-12-08 | 2023-12-09 | 2023-12-10
| User Story ID | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| 3 | As a user, I would like to start a game so that I can see the game board. | start controller | Jamie | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
|  |  | build cell and gameBoard models | Jamie | 1 | [5 empty] | 1 | 0
|  |  | start view | Jamie | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| 4 | As a user, I would like to click the buttons on the game board so that I can interact with the game. | complete view | Dakoda | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1
|  |  | complete controller | Dakoda | 4 | 0 | 0 | 0 | 0 | 0.5 | 3 | 0.5
| Ideal - Remaining efforts in uninterrupted working hours. |  |  |  | 11 | 11 | 10 | 9 | 7 | 5 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours. |  |  |  | 11 | 11 | 11 | 11 | 11 | 10.5 | 1.5 | 0
Project: | Minesweeper
Sprint # | 3
[5 empty] | DATE: | 2023-12-18 | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-24
| User Story ID | User Story | Task | Assigned To | Estimate (hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
| 5 | As a developer, I would like to remove full page refreshes in when a user click a cell on the game board so that I can save memory and create a smoother user experience. | Update Controllers | Dakoda | 1 | 0 | 0 | 0.5 | 0.5 | 0 | 0 | 0
|  |  | Complete Javascript | Dakoda | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0
|  |  | Complete Views | Dakoda | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0
| 6 | As a user, I would like right click on the game board to place a flag so that I can keep track of potential bombs on the board not be able to left click that cell. | Update JavaScript | Dakoda | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0
|  |  | Update Controllers | Dakoda | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0
| 7 | As a user, I would like it to display whether I win or lose a game so that I can see my results when the game is over. | Update View | Jamie | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
|  |  | Update Controller | Jamie | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| 8 | As a developer, I want to maintain a clean code base by performing occasional refactoring and cleanup | Build Game Logic Service (refactoring) | Jamie | 6 | 0 | 0 | 0 | 2 | 4 | 0 | 0
|  |  | Code Cleanup and commenting | Jamie | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
| Ideal - Remaining efforts in uninterrupted working hours. |  |  |  | 20 | 18 | 16 | 14 | 12 | 6 | 2 | 0
| Actual - Remaining efforts in uninterrupted working hours. |  |  |  | 20 | 20 | 20 | 15.5 | 8 | 2 | 0 | 0

## How To Use
Step 1 | Hold a Sprint Planning meeting on Day 1 of of your Sprint where you will complete or update your User Stories as well as (re)prioritize your User Stories in your Product Back Log (ideally this should be done for the next 3-4 Sprints)
Step 2 | Copy the User Stories you plan to complete for this Sprint into your Sprint Back Log
Step 3 | Copy the User Stories you plan to complete from your Sprint Back Log into Column C
Step 4 | Break the User Story into a series of step by step development tasks in Column D
Step 5 | Estimate the User Story (in 1, 2, 4 or 8 Effort Man Hours) in Column F and if the task is larger than 8 hours break the User Story into multiple User Stories
Step 6 | Assign the User Story to a single Team Member in Column E
Step 7 | Repeat steps 4-6 for each User Story that has been planned for this Sprint
Step 8 | At the end of each day each Team Member should update the effort hours that were worked on their User Story to burn their work down
Step 9 | After each Daily Standup each Team Member should review the Burn Down Chart to ensure your Sprint will be delivered on time